## Status Report 4
Status Report for Team 2
Project |  | Status: (Red/Yellow/Green)
Date: | 2026-10-08 | Overall Status: | Green
Contact: | Microsoft Teams | Explanation: | Polishing off code and mainly all working on presentation
Prepared By: | Kian
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Kian | Frontend, presentation
Alexandra | Presentation
Ahmed | Error Handling, presentation
Alanis | Presentation
ID # | Key Issues | Action Plan |  |  | Status
1 | Delay due to updated classes and related issues | Issues have been resolved; multiple people on remaining tasks |  |  | Currently resolving
2 | frontend too much like a wireframe | add relevant background image |  |  | to do
Critical Milestones |  | Health | Due Date | Status % | Comments
Planning |  | Green | 2026-10-05 | 100%
Frontend GUI |  | Green | 2026-10-06 | 100%
User Login |  | Red | 2026-10-07 | 0%
View Inventory |  | Green | 2026-10-06 | 100%
Update Inventory |  | Green | 2026-10-06 | 100%
Browse Cocktails |  | Green | 2026-10-07 | 100%
Add to Menu |  | Green | 2026-10-06 | 100%
View Menu |  | Green | 2026-10-06 | 100%
View Recipe |  | Green | 2026-10-06 | 100%
Automatically Manage Ingredients |  | Green | 2026-10-07 | 100%
Delete from Menu |  | Green | 2026-10-07 | 100%
Variance Report |  | Green | 2026-10-07 | 100%
Error Handling |  | Green | 2026-10-07 | 100%
Complete testing |  |  | 2026-10-08 | 100%
Dry Run |  | Green | 2026-10-08 | 100%
Presentation |  | Green | 2026-10-08 | 100%
Stretch Goals
Export Recipes |  | Green | 2026-10-08 | 0%
Access Permission |  | Green | 2026-10-08 | 0%
V2 Features
Price/cost implementation |  | Green

## Status Report 3
Status Report for Team 2
Project |  | Status: (Red/Yellow/Green)
Date: | 2026-10-07 | Overall Status: | Green
Contact: | Microsoft Teams | Explanation: | A lot of features have been implemented today. Remaining tasks can be completed by tomorrow
Prepared By: | Alanis Ballans
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Kian | Continuing GUI, debugging updated classes
Alexandra | Completed stock service, updated DTOs
Ahmed | Completed and tested cocktail service, updated DTOs and schema
Alanis | Created report and auth services + controllers, started report service + controller
ID # | Key Issues | Action Plan |  |  | Status
1 | Delay due to updated classes and related issues | Issues have been resolved; multiple people on remaining tasks |  |  | Currently resolving
Critical Milestones |  | Health | Due Date | Status % | Comments
Planning |  | Green | 2026-10-05 | 100%
Frontend GUI |  | Green | 2026-10-06 | 70%
User Login |  | Yellow | 2026-10-07 | 0%
View Inventory |  | Green | 2026-10-06 | 100%
Update Inventory |  | Green | 2026-10-06 | 100%
Browse Cocktails |  | Green | 2026-10-07 | 100%
Add to Menu |  | Green | 2026-10-06 | 100%
View Menu |  | Green | 2026-10-06 | 100%
View Recipe |  | Green | 2026-10-06 | 100%
Automatically Manage Ingredients |  | Green | 2026-10-07 | 100%
Delete from Menu |  | Green | 2026-10-07 | 100%
Variance Report |  | Green | 2026-10-07 | 60% | Finished by end of day today
Error Handling |  | Yellow | 2026-10-07 | 20%
Complete testing |  |  | 2026-10-08 | 40%
Dry Run |  | Green | 2026-10-08 | 0%
Presentation |  | Green | 2026-10-08 | 10%
Stretch Goals
Export Recipes |  | Green | 2026-10-08 | 0%
Access Permission |  | Green | 2026-10-08 | 0%
V2 Features
Price/cost implementation |  | Green

## Status Report 2
Status Report for Team 2
Project |  | Status: (Red/Yellow/Green)
Date: | 2026-10-06 | Overall Status: | Green
Contact: | Microsoft Teams | Explanation: | Working on service layer, dto and setting up public database
Prepared By: | Ahmed
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Kian | Created public database, edited class diagram, working on frontend
Alexandra | working on service layer
Ahmed | working on service layer and api logic
Alanis | Created dto and schema
ID # | Key Issues | Action Plan |  |  | Status
None
Critical Milestones |  | Health | Due Date | Status % | Comments
Planning |  | Green | 2026-10-05 | 100%
Frontend GUI |  | Green | 2026-10-06 | 65%
User Login |  | Green | 2026-10-07 | 0%
View Inventory |  | Green | 2026-10-06 | 80% | Nearly done
Update Inventory |  | Green | 2026-10-06 | 100%
Browse Cocktails |  | Green | 2026-10-07 | 0%
Add to Menu |  | Green | 2026-10-06 | 50% | Finished by end of day
View Menu |  | Green | 2026-10-06 | 0%
View Recipe |  | Green | 2026-10-06 | 0%
Automatically Manage Ingredients |  | Green | 2026-10-07 | 0%
Delete from Menu |  | Green | 2026-10-07 | 0%
Error Handling |  | Green | 2026-10-07 | 0%
Dry Run |  | Green | 2026-10-08 | 0%
Presentation |  | Green | 2026-10-08 | 0%
Stretch Goals
Export Recipes |  | Green | 2026-10-08 | 0%
Access Permission |  | Green | 2026-10-08 | 0%
V2 Features
Green

## Status Report 1
Status Report for Team 2
Project |  | Status: (Red/Yellow/Green)
Date: | 2026-10-05 | Overall Status: | Green
Contact: | Microsoft Teams | Explanation: | Working on requirements, feature list and diagrams.
Prepared By: | Alexandra
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Everyone | Discussing project requirements, working on project documentation
Alexandra | Set up repository and project, project report
Ahmed | Class diagram, ERD diagram start
Alanis | Class diagram, UX design started
Kian | Class diagram
ID # | Key Issues | Action Plan |  |  | Status
None
Critical Milestones |  | Health | Due Date | Status % | Comments
Planning |  | Green | 2026-10-05 | 100%
Frontend GUI |  | Green | 2026-10-06 | 0%
User Login |  | Green | 2026-10-07 | 0%
View Inventory |  | Green | 2026-10-06 | 0%
Update Inventory |  | Green | 2026-10-06 | 0%
Browse Cocktails |  | Green | 2026-10-07 | 0%
Add to Menu |  | Green | 2026-10-06 | 0%
View Menu |  | Green | 2026-10-06 | 0%
View Recipe |  | Green | 2026-10-06 | 0%
Automatically Manage Ingredients |  | Green | 2026-10-07 | 0%
Delete from Menu |  | Green | 2026-10-07 | 0%
Error Handling |  | Green | 2026-10-07 | 0%
Dry Run |  | Green | 2026-10-08 | 0%
Presentation |  | Green | 2026-10-08 | 0%
Stretch Goals
Export Recipes |  | Green | 2026-10-08 | 0%
Access Permission |  | Green | 2026-10-08 | 0%
V2 Features
Green